## Project Schedule
PROJECT SCHEDULE TEMPLATE
PROJECT NAME | Using Housing Data to Analyze Neighborhood Quality
PROJECT DELIVERABLE | User Interface that displays all the results.
SCOPE STATEMENT | This project investigates the key factors influencing property prices in the Miami real estate market, focusing on elements such as proximity to amenities, property characteristics, age-related depreciation, and seasonal trends.
START DATE | END DATE | OVERALL PROGRESS
2025-06-02 | 2025-08-04 | 10%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
Set Kickoff Meeting | Esha C. & Ishan C. | 2025-06-01 | 2025-06-02 | 2 | Complete
Agree on Objectives | Esha C. & Ishan C. | 2025-06-04 | 2025-06-06 | 3 | Complete
Extracting detailed features from objectives | Esha C. & Ishan C. | 2025-06-07 | 2025-06-09 | 3 | Complete
Data pre-processing and cleaning | Esha C. & Ishan C. | 2025-06-10 | 2025-06-16 | 7 | Not Started
Exploratory Data Analysis and Visualizations for first two features | Esha C. & Ishan C. | 2025-06-17 | 2025-06-23 | 7 | Not Started
Exploratory Data Analysis and Visualizations for next two features | Esha C. & Ishan C. | 2025-06-24 | 2025-07-01 | 7 | Not Started
Creating the user interface to display results | Esha C. & Ishan C. | 2025-07-02 | 2025-07-12 | 10 | Not Started
Results analysis | Esha C. & Ishan C. | 2025-07-14 | 2025-07-18 | 4 | Not Started
Presentation | Esha C. & Ishan C. | 2025-07-19 | 2025-07-28 | 8 | Not Started